## Sheet1
What went well | What didn't go well | Anything we can improve? | Action Points
Mobbing the back-end at the start, so everyone understands it - Iain | Didn't achieve all of the MVP, i.e. updates - Iain | Being more willing to make big changes to plans as things we approach new stages in the project - Mark | mob for unified understanding of stuff
Planning for the backend went well - Mark | Continuous planning Paulo | Investigate more node modules in the future that might have made our lives easier - Mark | Planning more (detailed, all on the same page x2, good tooling) makes things easier to change later on x2
Making changes to the databases & backend proved easier than expected - Mark | Underestimated how complex React was given how easy Vue was to use - Mark | Stay more focused on the MVP. Paulo | be prepped for presentation
Initial Plan Paulo | Final product still a little buggy, i.e. double-booking - Iain | Could have asked for more help from the instructors, or asked sooner to speed up the progress - Iain | working at a sustainable pace
Presentation Paulo | I got too obessed with adding more and more filtering functionality to the backend that didn't end up getting used on the frontend - Mark | Could have spent more time refactoring vs styling improvements - Mark | clear communication regarding work
Time comitments put in. 6 days on 1 day off. Paulo | Debugging, simple as unplug your mouse. huh? Paulo |  | PR's YEAH!
Good work/life balance - Iain | Iain went crazy and got depressed when things weren't working (setState is asynchronous!) - Iain |  | Stay more focused on the MVP
We did a good job keeping in touch with each other & stuck to our time commitments - Mark | I shouldn't be as prejiduice & narrow minded against Modals due to bad past experiences when React has some good modules to help work with them - Mark |  | dont forget to plan the front end thoroughly
Alan found some fantastic software that helped with out planning - Mark |  |  | look into possible react tooling for next time
No one in the group was excluded from contributing ideas or shouted down - Mark |  |  | try to stay more focused on mvp tasks
There weren't any fights or huge personality clashses - Mark |  |  | use consistent hardware for testing
Pull requests were promtly reviewed so no one's work was left hanging - Mark |  |  | dont throw yourself at a problem for too long
more research into different technologies
Either investigate Redux (very heavy) to assist with passing state in React or look into MobX which is lighter than Redux, https://mobx.js.org/README.html